## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Vaibhavi Kapse
Document Created On: | 2024-07-08
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Data Analytics on Student Insights |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Student Interns Analysis
PROJECT SCOPE
PROJECT START DATE | 2024-06-12
PROJECT END DATE | 2024-07-09
OVERALL PROGRESS | Done
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2024-06-12 | 2024-06-13 | 2 | COMPLETED
| 1.2 Create a project charter |  | 2023-03-14 | 2024-06-16 | 2 | COMPLETED
| 1.3 Requirement gathering |  | 2023-06-17 | 2024-06-20 | 3 | COMPLETED
2 Planning
| 2.1 Baseline project plan |  | 2024-06-20 | 2024-06-23 | 3 | COMPLETED
| 2.2 Plan the design,methods |  | 2024-06-23 | 2024-06-27 | 3 | COMPLETED
3 Execution
| 3.1 Developing |  | 2024-06-28 | 2024-06-02 | 5 | COMPLETED
| 3.2 Testing |  | 2024-07-02 | 2024-07-04 | 3 | COMPLETED
| 3.3 Deployment |  | 2024-07-05 | 2024-07-08 | 6 | COMPLETED
| 4 Closure |  | 2024-07-09 | 2024-07-09 | 1 | COMPLETED